## Portfolio Summary
Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project
Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project | Pomona Drinks Inventory Availability Improvement Project
Project Manager | Agnes Iwaye |  | PROJECT MANAGEMENT APPROACH | PROJECT MANAGEMENT APPROACH | PROJECT MANAGEMENT APPROACH | PROJECT MANAGEMENT APPROACH | PROJECT MANAGEMENT APPROACH
Client | Pomona Drinks (illustrative) |  | 1. Diagnose — Reviewed monthly orders, receipts, shipments and peak-period patterns.
Operation | Inbound receipt, two-pack kitting, warehousing, outbound fulfillment and last-mile delivery |  | 2. Define — Established minimum stock, safety stock and reorder points by SKU.
Business problem | Peak-season demand repeatedly depleted warehouse inventory, interrupting packing and deliveries to retail stores. |  | 3. Build — Created a live inventory tracker with red/amber/green conditional alerts.
Goal | Prevent stockouts while supporting higher festive-period delivery volume. |  | 4. Implement — Aligned warehouse and client replenishment decisions to alert thresholds.
Solution | Built SKU-level monthly benchmarks, reorder points, weeks-of-cover measures and conditional alerts using historical demand patterns. |  | 5. Monitor — Tracked fill rate, stockouts, weeks of cover, forecast accuracy and delivery volume.
Outcome | Illustrative model shows zero stockout events in the post-implementation period and delivery volume approximately doubling during the peak comparison window. |  | 6. Improve — Adjusted peak multipliers and benchmarks based on actual consumption.

## Dashboard
Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard
Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard | Supply Chain Performance Dashboard
Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data | Baseline: Jan–Jun 2025 ¦ Improved process: Jul–Dec 2025 ¦ Synthetic portfolio data
POST-PROCESS FILL RATE |  |  | STOCKOUT UNITS |  |  | ON-TIME DELIVERY RATE |  |  | PEAK VOLUME GROWTH
100% |  |  | 0 |  |  | 97.98% |  |  | 95.93%
Month | Demand | Shipped | Fill Rate | Stockout Units
Jan | 4180 | 3761 | 89.98% | 419
Feb | 4215 | 3794 | 90.01% | 421
Mar | 4220 | 3799 | 90.02% | 421
Apr | 4188 | 3768 | 89.97% | 420
May | 4169 | 3753 | 90.02% | 416
Jun | 4229 | 3806 | 90% | 423
Jul | 5265 | 5265 | 100% | 0
Aug | 4169 | 4169 | 100% | 0
Sep | 4167 | 4167 | 100% | 0
Oct | 4213 | 4213 | 100% | 0
Nov | 7366 | 7366 | 100% | 0
Dec | 7444 | 7444 | 100% | 0
SKU | On Hand | On Order | Reorder Point | Weeks Cover | Alert
Original 12oz | 1180 | 900 | 914.8833 | 5.5214 | GREEN - Sufficient
Ginger 12oz | 710 | 600 | 801.8 | 4.4347 | GREEN - Sufficient
Mango 12oz | 520 | 800 | 796.25 | 4.9733 | GREEN - Sufficient
Berry 12oz | 980 | 0 | 612.85 | 3.8835 | AMBER - Monitor
Zero Sugar 12oz | 430 | 650 | 699.9667 | 4.8492 | GREEN - Sufficient
Variety Pack | 650 | 900 | 855.6333 | 4.917 | GREEN - Sufficient

## Inventory Tracker
Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker
Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker | Live Inventory & Replenishment Alert Tracker
Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically. | Update blue input cells (On Hand, On Order, Lead Time). Formulas and alerts will recalculate automatically.
SKU | Current On Hand | On Order | Avg Monthly Demand | Peak Multiplier | Peak Forecast | Lead Time (days) | Daily Demand | Safety Stock | Reorder Point | Inventory Position | Weeks of Cover | Recommended Order | Alert | Action
Original 12oz | 1180 | 900 | 1033.5 | 1.5622 | 1614.5 | 10 | 53.8167 | 376.7167 | 914.8833 | 2080 | 5.5214 | 342 | GREEN - Sufficient | No action
Ginger 12oz | 710 | 600 | 825.8333 | 1.533 | 1266 | 12 | 42.2 | 295.4 | 801.8 | 1310 | 4.4347 | 589 | GREEN - Sufficient | No action
Mango 12oz | 520 | 800 | 758 | 1.5007 | 1137.5 | 14 | 37.9167 | 265.4167 | 796.25 | 1320 | 4.9733 | 387 | GREEN - Sufficient | No action
Berry 12oz | 980 | 0 | 693.25 | 1.56 | 1081.5 | 10 | 36.05 | 252.35 | 612.85 | 980 | 3.8835 | 643 | AMBER - Monitor | Review in 48 hours
Zero Sugar 12oz | 430 | 650 | 617.4167 | 1.546 | 954.5 | 15 | 31.8167 | 222.7167 | 699.9667 | 1080 | 4.8492 | 352 | GREEN - Sufficient | No action
Variety Pack | 650 | 900 | 890.75 | 1.5167 | 1351 | 12 | 45.0333 | 315.2333 | 855.6333 | 1550 | 4.917 | 477 | GREEN - Sufficient | No action

## Historical Data
Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data
Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data | Historical Fulfillment Dataset — Synthetic Portfolio Data
Month | SKU | Opening Units | Received Units | Available Units | Demand Units | Shipped Units | Closing Units | Stockout Units | Orders | Orders Fulfilled | Fill Rate | On-Time Deliveries | Forecast Units | Forecast Accuracy
2025-01-01 | Original 12oz | 520 | 241 | 761 | 846 | 761 | 0 | 85 | 14 | 12 | 89.95% | 11 | 694 | 82.03%
2025-01-01 | Ginger 12oz | 430 | 250 | 680 | 756 | 680 | 0 | 76 | 13 | 11 | 89.95% | 10 | 627 | 82.94%
2025-01-01 | Mango 12oz | 390 | 222 | 612 | 680 | 612 | 0 | 68 | 11 | 9 | 90% | 8 | 571 | 83.97%
2025-01-01 | Berry 12oz | 360 | 185 | 545 | 606 | 545 | 0 | 61 | 10 | 8 | 89.93% | 7 | 515 | 84.98%
2025-01-01 | Zero Sugar 12oz | 330 | 152 | 482 | 535 | 482 | 0 | 53 | 9 | 8 | 90.09% | 7 | 460 | 85.98%
2025-01-01 | Variety Pack | 450 | 231 | 681 | 757 | 681 | 0 | 76 | 13 | 11 | 89.96% | 10 | 659 | 87.05%
2025-02-01 | Original 12oz | 0 | 818 | 818 | 909 | 818 | 0 | 91 | 15 | 13 | 89.99% | 11 | 754 | 82.95%
2025-02-01 | Ginger 12oz | 0 | 642 | 642 | 713 | 642 | 0 | 71 | 12 | 10 | 90.04% | 9 | 599 | 84.01%
2025-02-01 | Mango 12oz | 0 | 576 | 576 | 640 | 576 | 0 | 64 | 11 | 9 | 90% | 8 | 544 | 85%
2025-02-01 | Berry 12oz | 0 | 513 | 513 | 570 | 513 | 0 | 57 | 10 | 9 | 90% | 8 | 490 | 85.96%
2025-02-01 | Zero Sugar 12oz | 0 | 515 | 515 | 572 | 515 | 0 | 57 | 10 | 9 | 90.03% | 8 | 498 | 87.06%
2025-02-01 | Variety Pack | 0 | 730 | 730 | 811 | 730 | 0 | 81 | 14 | 12 | 90.01% | 11 | 714 | 88.04%
2025-03-01 | Original 12oz | 0 | 770 | 770 | 855 | 770 | 0 | 85 | 14 | 12 | 90.06% | 11 | 718 | 83.98%
2025-03-01 | Ginger 12oz | 0 | 687 | 687 | 763 | 687 | 0 | 76 | 13 | 11 | 90.04% | 10 | 649 | 85.06%
2025-03-01 | Mango 12oz | 0 | 617 | 617 | 686 | 617 | 0 | 69 | 11 | 9 | 89.94% | 8 | 590 | 86.01%
2025-03-01 | Berry 12oz | 0 | 551 | 551 | 612 | 551 | 0 | 61 | 10 | 8 | 90.03% | 7 | 532 | 86.93%
2025-03-01 | Zero Sugar 12oz | 0 | 486 | 486 | 540 | 486 | 0 | 54 | 9 | 8 | 90% | 7 | 475 | 87.96%
2025-03-01 | Variety Pack | 0 | 688 | 688 | 764 | 688 | 0 | 76 | 13 | 11 | 90.05% | 10 | 680 | 89.01%
2025-04-01 | Original 12oz | 0 | 826 | 826 | 918 | 826 | 0 | 92 | 15 | 13 | 89.98% | 11 | 780 | 84.97%
2025-04-01 | Ginger 12oz | 0 | 648 | 648 | 720 | 648 | 0 | 72 | 12 | 10 | 90% | 9 | 619 | 85.97%
2025-04-01 | Mango 12oz | 0 | 582 | 582 | 647 | 582 | 0 | 65 | 11 | 9 | 89.95% | 8 | 563 | 87.02%
2025-04-01 | Berry 12oz | 0 | 518 | 518 | 576 | 518 | 0 | 58 | 10 | 9 | 89.93% | 8 | 507 | 88.02%
2025-04-01 | Zero Sugar 12oz | 0 | 457 | 457 | 508 | 457 | 0 | 51 | 8 | 7 | 89.96% | 6 | 452 | 88.98%
2025-04-01 | Variety Pack | 0 | 737 | 737 | 819 | 737 | 0 | 82 | 14 | 12 | 89.99% | 11 | 737 | 89.99%
2025-05-01 | Original 12oz | 0 | 778 | 778 | 864 | 778 | 0 | 86 | 14 | 12 | 90.05% | 11 | 743 | 86%
2025-05-01 | Ginger 12oz | 0 | 609 | 609 | 677 | 609 | 0 | 68 | 11 | 9 | 89.96% | 8 | 589 | 87%
2025-05-01 | Mango 12oz | 0 | 624 | 624 | 693 | 624 | 0 | 69 | 12 | 10 | 90.04% | 9 | 610 | 88.02%
2025-05-01 | Berry 12oz | 0 | 556 | 556 | 618 | 556 | 0 | 62 | 10 | 8 | 89.97% | 7 | 550 | 89%
2025-05-01 | Zero Sugar 12oz | 0 | 491 | 491 | 545 | 491 | 0 | 54 | 9 | 8 | 90.09% | 7 | 490 | 89.91%
2025-05-01 | Variety Pack | 0 | 695 | 695 | 772 | 695 | 0 | 77 | 13 | 11 | 90.03% | 10 | 633 | 81.99%
2025-06-01 | Original 12oz | 0 | 834 | 834 | 927 | 834 | 0 | 93 | 15 | 13 | 89.97% | 11 | 806 | 86.95%
2025-06-01 | Ginger 12oz | 0 | 654 | 654 | 727 | 654 | 0 | 73 | 12 | 10 | 89.96% | 9 | 640 | 88.03%
2025-06-01 | Mango 12oz | 0 | 588 | 588 | 653 | 588 | 0 | 65 | 11 | 9 | 90.05% | 8 | 581 | 88.97%
2025-06-01 | Berry 12oz | 0 | 524 | 524 | 582 | 524 | 0 | 58 | 10 | 9 | 90.03% | 8 | 524 | 90.03%
2025-06-01 | Zero Sugar 12oz | 0 | 462 | 462 | 513 | 462 | 0 | 51 | 9 | 8 | 90.06% | 7 | 421 | 82.07%
2025-06-01 | Variety Pack | 0 | 744 | 744 | 827 | 744 | 0 | 83 | 14 | 12 | 89.96% | 11 | 686 | 82.95%
2025-07-01 | Original 12oz | 0 | 3071 | 3071 | 1091 | 1091 | 1980 | 0 | 18 | 18 | 100% | 17 | 1113 | 97.98%
2025-07-01 | Ginger 12oz | 0 | 2439 | 2439 | 855 | 855 | 1584 | 0 | 14 | 14 | 100% | 14 | 821 | 96.02%
2025-07-01 | Mango 12oz | 0 | 2327 | 2327 | 875 | 875 | 1452 | 0 | 15 | 15 | 100% | 15 | 849 | 97.03%
2025-07-01 | Berry 12oz | 0 | 2100 | 2100 | 780 | 780 | 1320 | 0 | 13 | 13 | 100% | 13 | 764 | 97.95%
2025-07-01 | Zero Sugar 12oz | 0 | 1877 | 1877 | 689 | 689 | 1188 | 0 | 11 | 11 | 100% | 11 | 682 | 98.98%
2025-07-01 | Variety Pack | 0 | 2691 | 2691 | 975 | 975 | 1716 | 0 | 16 | 16 | 100% | 16 | 975 | 100%
2025-08-01 | Original 12oz | 1980 | 306 | 2286 | 936 | 936 | 1350 | 0 | 16 | 16 | 100% | 16 | 899 | 96.05%
2025-08-01 | Ginger 12oz | 1584 | 230 | 1814 | 734 | 734 | 1080 | 0 | 12 | 12 | 100% | 12 | 712 | 97%
2025-08-01 | Mango 12oz | 1452 | 198 | 1650 | 660 | 660 | 990 | 0 | 11 | 11 | 100% | 11 | 647 | 98.03%
2025-08-01 | Berry 12oz | 1320 | 168 | 1488 | 588 | 588 | 900 | 0 | 10 | 10 | 100% | 10 | 582 | 98.98%
2025-08-01 | Zero Sugar 12oz | 1188 | 140 | 1328 | 518 | 518 | 810 | 0 | 9 | 9 | 100% | 9 | 518 | 100%
2025-08-01 | Variety Pack | 1716 | 187 | 1903 | 733 | 733 | 1170 | 0 | 12 | 12 | 100% | 12 | 740 | 99.05%
2025-09-01 | Original 12oz | 1350 | 882 | 2232 | 882 | 882 | 1350 | 0 | 15 | 15 | 100% | 15 | 856 | 97.05%
2025-09-01 | Ginger 12oz | 1080 | 691 | 1771 | 691 | 691 | 1080 | 0 | 12 | 12 | 100% | 12 | 677 | 97.97%
2025-09-01 | Mango 12oz | 990 | 620 | 1610 | 620 | 620 | 990 | 0 | 10 | 10 | 100% | 10 | 614 | 99.03%
2025-09-01 | Berry 12oz | 900 | 630 | 1530 | 630 | 630 | 900 | 0 | 11 | 11 | 100% | 11 | 630 | 100%
2025-09-01 | Zero Sugar 12oz | 810 | 556 | 1366 | 556 | 556 | 810 | 0 | 9 | 9 | 100% | 9 | 562 | 98.92%
2025-09-01 | Variety Pack | 1170 | 788 | 1958 | 788 | 788 | 1170 | 0 | 13 | 13 | 100% | 13 | 804 | 97.97%
2025-10-01 | Original 12oz | 1350 | 945 | 2295 | 945 | 945 | 1350 | 0 | 16 | 16 | 100% | 16 | 926 | 97.99%
2025-10-01 | Ginger 12oz | 1080 | 742 | 1822 | 742 | 742 | 1080 | 0 | 12 | 12 | 100% | 12 | 735 | 99.06%
2025-10-01 | Mango 12oz | 990 | 667 | 1657 | 667 | 667 | 990 | 0 | 11 | 11 | 100% | 11 | 667 | 100%
2025-10-01 | Berry 12oz | 900 | 594 | 1494 | 594 | 594 | 900 | 0 | 10 | 10 | 100% | 10 | 600 | 98.99%
2025-10-01 | Zero Sugar 12oz | 810 | 524 | 1334 | 524 | 524 | 810 | 0 | 9 | 9 | 100% | 9 | 534 | 98.09%
2025-10-01 | Variety Pack | 1170 | 741 | 1911 | 741 | 741 | 1170 | 0 | 12 | 12 | 100% | 12 | 711 | 95.95%
2025-11-01 | Original 12oz | 1350 | 2189 | 3539 | 1559 | 1559 | 1980 | 0 | 26 | 26 | 100% | 25 | 1543 | 98.97%
2025-11-01 | Ginger 12oz | 1080 | 1726 | 2806 | 1222 | 1222 | 1584 | 0 | 20 | 20 | 100% | 19 | 1222 | 100%
2025-11-01 | Mango 12oz | 990 | 1559 | 2549 | 1097 | 1097 | 1452 | 0 | 18 | 18 | 100% | 17 | 1108 | 99%
2025-11-01 | Berry 12oz | 900 | 1533 | 2433 | 1113 | 1113 | 1320 | 0 | 19 | 19 | 100% | 18 | 1135 | 98.02%
2025-11-01 | Zero Sugar 12oz | 810 | 1361 | 2171 | 983 | 983 | 1188 | 0 | 16 | 16 | 100% | 16 | 944 | 96.03%
2025-11-01 | Variety Pack | 1170 | 1938 | 3108 | 1392 | 1392 | 1716 | 0 | 23 | 23 | 100% | 22 | 1350 | 96.98%
2025-12-01 | Original 12oz | 1980 | 1670 | 3650 | 1670 | 1670 | 1980 | 0 | 28 | 28 | 100% | 27 | 1670 | 100%
2025-12-01 | Ginger 12oz | 1584 | 1310 | 2894 | 1310 | 1310 | 1584 | 0 | 22 | 22 | 100% | 21 | 1323 | 99.01%
2025-12-01 | Mango 12oz | 1452 | 1178 | 2630 | 1178 | 1178 | 1452 | 0 | 20 | 20 | 100% | 19 | 1202 | 97.96%
2025-12-01 | Berry 12oz | 1320 | 1050 | 2370 | 1050 | 1050 | 1320 | 0 | 18 | 18 | 100% | 17 | 1008 | 96%
2025-12-01 | Zero Sugar 12oz | 1188 | 926 | 2114 | 926 | 926 | 1188 | 0 | 15 | 15 | 100% | 15 | 898 | 96.98%
2025-12-01 | Variety Pack | 1716 | 1310 | 3026 | 1310 | 1310 | 1716 | 0 | 22 | 22 | 100% | 21 | 1284 | 98.02%

## KPI Definitions
KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules
KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules | KPI Dictionary & Management Rules
KPI | Definition | Formula | Target | Frequency | Owner | Management Use
Order Fill Rate | Share of requested units shipped | Units shipped / Demand units | >= 98% | Weekly | Warehouse PM | Shows ability to satisfy customer demand
Stockout Units | Demand units not shipped | MAX(0, Demand - Shipped) | 0 | Daily | Inventory Lead | Triggers replenishment escalation
Weeks of Cover | Time inventory can support forecast demand | Inventory position / Weekly demand | 4–8 weeks | Weekly | Warehouse PM | Balances availability and excess stock
Reorder Point | Inventory level that triggers replenishment | Lead-time demand + Safety stock | SKU-specific | Weekly | Planner | Prevents depletion before inbound stock arrives
Forecast Accuracy | Closeness of forecast to actual demand | 1 - ABS(Forecast - Actual) / Actual | >= 90% | Monthly | Project Manager | Improves peak-season planning
On-Time Delivery Rate | Fulfilled orders delivered on time | On-time deliveries / Orders fulfilled | >= 95% | Weekly | Delivery Lead | Measures last-mile reliability
Inventory Turnover | Demand consumed relative to average inventory | Annual demand / Average inventory | Monitor trend | Monthly | Operations | Identifies slow or overstocked inventory
Peak Volume Growth | Change in peak shipments vs comparison period | Peak shipped / Baseline shipped - 1 | >= 50% | Seasonal | Project Manager | Demonstrates capacity and sales enablement
Alert Response Time | Time from red alert to action | Action timestamp - Alert timestamp | < 24 hours | Per alert | Project Manager | Measures responsiveness to risk