## Slide 1
PROJECT MANAGEMENT PORTFOLIO
Building government relationships into institutional influence
Stakeholder Management Case Study
Bobby Dodd Institute
<10
political stakeholders
at project start
150+
stakeholders engaged
by Year 3
Agnes Iwaye | Project Manager

## Slide 2
The challenge was not access—it was a repeatable engagement system
02
Starting point
Fewer than 10 political stakeholders
Limited relationship coverage reduced the organization’s ability to secure site visits, participate consistently in legislative activity, and build sustained government support.
Project response
A structured stakeholder-management program
Identify relevant public officials and staff
Map influence, interest, and relationship status
Tailor communication by stakeholder need
Create follow-up discipline and engagement records
Convert awareness into visits, advocacy, and support
Notes: Explain that the core problem was a lack of system and coverage. Your contribution was a scalable operating rhythm.
[Sources]
- User-provided project facts and metrics from Agnes Iwaye; no external sources used.
[/Sources]

## Slide 3
Structured outreach expanded the network more than fifteenfold
03
Chart: 
| Starting point | Year 1 | Year 2 | Year 3
Political stakeholders | 9 | 20 | 100 | 150
15×+
network growth
from fewer than 10 to 150+
Year 1
Build credibility and learn the landscape
Years 2–3
Scale relationships and activate stakeholder support

## Slide 4
The stakeholder map matched effort to influence and interest
04
HIGH INTEREST
LOW INTEREST
LOW INFLUENCE
HIGH INFLUENCE
KEEP INFORMED
MANAGE CLOSELY
• District and legislative staff
• Coalition and advocacy partners
• Local elected officials
• Community leaders
• Committee chairs and legislators
• Agency and executive leaders
• Grant decision-makers
• Senior policy staff
MONITOR & DEVELOP
KEEP SATISFIED
• Emerging candidates
• New legislative staff
• Community advocates
• Prospective allies
• Appropriations stakeholders
• Executive offices
• Senior agency contacts
• Institutional partners

## Slide 5
A segmented communication plan created consistency without losing relevance
05
The plan defined what each group needed to know, the desired action, and the follow-up cadence.
Stakeholder group | Engagement objective | Primary channel | Cadence | Success measure
Legislators & committee leaders | Build sponsorship and policy support | Briefings, session meetings, site visits | Monthly + session-based | Meeting, visit, public support
Legislative staff | Maintain working relationships and issue awareness | Email updates, calls, briefing materials | Biweekly in session | Response and follow-up action
Agencies & executive offices | Align BDI goals with public priorities | Executive briefings, proposals, reports | Quarterly | Program or funding alignment
Local officials | Build district-level visibility | Events, tours, community updates | Quarterly | Referral, attendance, endorsement
Coalition partners | Coordinate shared advocacy and campaigns | Working groups, campaign meetings | Monthly | Joint action completed

## Slide 6
Clear ownership prevented stakeholder relationships from going dormant
06
R = Responsible | A = Accountable | C = Consulted | I = Informed
Engagement activity | Project Manager | Executive Lead | Program Lead | Comms | Development
Identify and prioritize stakeholders | R/A | C | C | I | C
Prepare stakeholder briefing | R | A | C | C | I
Coordinate legislative meeting | R | A | I | C | I
Host site visit | R | A | R | C | C
Campaign or advocacy engagement | R | A | C | R | I
Grant/funding follow-up | C | A | C | I | R
Document next steps and follow-up | R/A | I | C | I | C

## Slide 7
A five-stage operating rhythm converted contacts into sustained support
07
1 IDENTIFY
Research officials, staff, committees and policy alignment.
2 PRIORITIZE
Score influence, interest, access and relationship maturity.
3 ENGAGE
Tailor messages, schedule meetings and manage communications.
4 ACTIVATE
Secure site visits, campaigns, session participation and visible support.
5 SUSTAIN
Record commitments, follow up, report progress and deepen trust.
Feedback loop
Each interaction updated the stakeholder map, communication plan and next-best action.

## Slide 8
Relationship growth translated into institutional visibility and support
08
The project produced measurable network growth and concrete government-relations outcomes.
150+
political stakeholders engaged by Year 3
15×+
network growth from the starting point
1
Georgia House resolution recognizing BDI
Additional outcomes
Legislative-session participation • Political campaign engagement • Stakeholder site visits • Government buy-in • Grant support: [insert verified amount]